## Home
VSM Overview
The VSM objective is:
The complete elimination of waste so that all activities along a value stream create value from the perspective of the Consumer and/or Customer.
VSM provides a detailed, graphical depiction of actual flow of materials and information through a supply network providing total lead time as well as Value Added Time in order to reduce waste and enable flow.
•VALUE – what Customers/Consumers are willing to pay for.
•VALUE STREAM – the set of all actions (Value-Added and Non Value-Added) required to provide a specific product from:
•Concept to launch.
•Order to delivery.
•Raw materials to finished product in the hands of the Consumer.
•FLOW – organizing the Value Stream to be continuous.
•PULL – responding to downstream Customer demand at each point in the Value Stream.
•PERFECTION – relentless continuous improvement (culture).
•REPLENISHMENT STREAMS – linked to the 4 different Customer Demand Signals
•VALUE IS ADDED any time we physically change our product towards what the Customer is buying.
•NON VALUE ADDED is any activity that adds time and cost but is no necessary to meet Customer / Consumer needs.
•NON VALUE ADDED BUT REQUIRED: does not add value to the product but is necessary (i.e. regulations).
Value Stream Mapping enables systemic elimination of waste
Current
Ideal
Future
Current State Map represents existing conditions and reveals wastes and their sources.
Ideal State Map sets a very ambitious future state that takes into consideration Customer needs and challenges paradigms.
Future State Map represents a 2-3 year vision of what’s possible to improve the business towards Ideal.

## Legend
DATA BOXES
LEGEND
*Manuel Info Flow
*Digital Info Flow
*Material Flow
*Pushed Material Flow
*Pull Withdrawal
Shipping Method:
Customer
Name:
Monthly Demand:
Daily Demand:
Signal to ship
Shipping Frequency
Transit Time:
Inventory (units):
3 Key opportunities: -
-
-
% Unplanned DT:
Process
Process Name:
Start-up signal:
Completion signal:
# of op/shift:
# shifts:
Cycle Time:
Flow Time:
3 Key opportunities: -
-
-
% Scrap:
Standard in process stock:
Lead Time to order (Firm zone):
Materials
Material Name:
Supplier:
Method of Delivery:
Delivery Capability(daily,weekly etc):
Total FG per pallet( or other UOM):
Lot size:
# touches recipt use
3 Key opportunities: -
-
-
Inventory (units)
*Truck Shipment
*Inventory
S:Weekly
*Schedule :
*Buffer/Safety Stock
FIFO
*Airway Transport
*Maritime Transport
*Train Transport
FLOWS
SHIPMENT TYPES
*Kaizen Idea
NODES
Stock & Delivery
*Service Level Agreement Flow
External
Internal
*Forklift
*Operator
*Iteration rework
OPERATION
*Incoming materials are transferred to outbound without a process
*First in First out flow of material
*Delay
*Milk Run
*Supermarket This is a stockpoint where downstream customers can come for what they need.

## VSM Objective
Value Stream:
Date:
Team:
Business Case Why ? | Value Statement What is the Mission? | Boundaries What is the Scope? | Key Requirements Key Objectives - Musts ? | Measurements 2-3 Performance Indicators ? | Ideal Goal Ideal State Principles ?
Notes:

## Current State
_________ P&G ___________ CURRENT STATE
Total Lead Time
Total Lead Time
Value Added Lead Time
Non-Value Added Lead Time
IBL and Supplier
Making
Packing + Takeaway
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Soni, Aniket - Pictures of Current State attached

## Ideal State
_____ P&G ___________ IDEAL STATE
one pager
unıt prıce one pager
Total Lead Time
1
Day
LEAD
TIME:
Average Material LT
(Order etc..)
0.17
Days
Loading & Transit time
2 Days
0.02
Days
Total Lead Time
Value Added Lead Time
E2E IBL to Takeaway
Note on AU25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Soni, Aniket - Ideal State attached

## Future State
_____ P&G ___________ FUTURE STATE
one pager
unıt prıce one pager
Total Lead Time
1
Day
LEAD
TIME:
Average Material LT
(Order etc..)
0.17
Days
Loading & Transit time
2 Days
0.02
Days
Total Lead Time
Value Added Lead Time
IBL and Supplier
Packing + LTakeaway
Note on AX57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Soni, Aniket @Phumitanon, Chayute - - Missing Making, can you help to upload the picture of Making for Future State

## Q&A
Q&A SHEET

## Datasheet
DATA SHEET

## Action Plan
ACTION PLAN
0 |  |  |  | Service/Cost/Cash
No | Supply Chain Area | Loss | Frequency | Size of Prize | Impact | Reason/Source of Loss | Kaizen/Change | Action Description | Owner | Due Date | Status
1 | Operating strategy | Pre plan delay | Daily |  | 4 hours | Waiting for PM supportability from Supplier | Supplier confirmation vs. Supplier managed | Maintain Supplier Confirmation until we can automate using OMP-IVY visisbility, or a bridging solution for visibility supplier to provide accurate information on inventory / provide confirmation Confirmation of supportability from the supplier is required by 11:30 IST Shippers and Labels drive 70-80% of our daily material gaps, we need material safety and PDT interventions here 1) Label can we reduce the PDT like 2 or 3 days after the 1st SOP 2) Shippers can we increases the safety for all lines as PTF lines To ensure timely submission of the production plan to the plant, we need a faster reply from the supplier | Shivangi MSM | ASAP
2 | Packing | Change over Time | Daily |  |  | Change Over time loss | Dual transfer tank | Instal Dual tank in all the packing line | Boston
3 | Packing - Operating strategy | Pre plan delay | Daily |  | 4 hours | PM Gap | Shippers and Labels drive 70-80% of our daily material gaps, we need material safety and PDT interventions here 1) Label can we reduce the PDT like 2 or 3 days after the 1st SOP 2) Shippers can we increases the safety for all lines as PTF lines | To ensure timely submission of the production plan to the plant, we need a faster reply from the supplier | MSM, Aniket and Shivangi
4 | Packing - Planning | EOPQ | Daily | Service Touches |  | Capacity Loss at Packing or Making | Work process improvement in streamlining the communication for EO/PQ requirement Close EO/PQ requirement during launch gate |  | Nancy | JAS'26
5 | Packing - Planning | Extra Material trigger | Daily |  |  | Supplier capacity loss | Remove infinite batches inside Seq Zone, later for all as material part is solved | This avoids unnecessary or incorrect demand being sent to the supplier | Divya | June '26
6 | Packing - Planning | PM gap | Daily |  |  | PM gap in MFZ | Material check functionality in OMP, consult GH on OMP functionality SFA Integrated Planner | Will reduce the PM shortage inside MFZ | Divya | May '26
7 | Packing - Planning | Incorrect GR Parameter |  | Inventory | 3days | GR assumption not equal to demonstrated time | SLEA Parameter audit | Change to 1 day GR time SIP - check weekly on MRP vs PO [purchasing] data. To perform 3 way audit, PSM can use the global dashboard (recently implemented) to ensure the SLEA is consistent with PO data | Shivangi/Uma | May '26
8 | Packing - Planning | 1st order GR time | New PM |  |  | Insufficient time for QA release for 1st CMC lot | Systemic fix of incorporating 3days GR time in system | Include 3 days GR time in 1st order PDT or Maintain 3 days GR for 1st order and later change to ongoing | DONE
9 | Packing - Planning | Non-adherance to 100% MOST | New PI |  |  | Non identification of initiative code in OMP | Align operating strategy for initiatives (vs. base) prioritization strategy during constraint period | Seek consultation with Emma on possible solution in OMP; Seek discussion and alignment with Manik/Aniket, using MOST/PCD strategy as input if need to prioritize | Lidhin, Nancy
10 | QA | E-COA failures | Daily | SCLT Productivity | 4 hours + 1 FTE | Technical standard does not match the e-COA release for bottles | 100% E-COA/eliminate QA sampling/testing | Individualize the technical specs for each PMs in Enovia tp accommodate E-COA | Naphat (QA) -> PM R&D
11 | QA Leadtime | Additional time spent for QA Sampling and testing | Daily |  | 4 hours | smaller quantities result to higher frequency/sampling size to work on | Increase the packaging qty/size for RMs (not the MOQ) |  | MSM. QA
12 | RPM Warehouse | RPM WH Congestion | Daily |  | 4000 pallet to 600 pallets | Shipper Supplier PDT = 6 days; no space to keep inventory | Implement NSW or SMOI (Supplier WH near site) --> reduce WH inventory to release space | Discuss option as a contract option change with supplier | MSM | Review by Sep '26
13 | RPM Warehouse | UPI/Orange quantity for PMs | Daily |  | 22% UPI PM = xx days | Inventory with no future demand | UPI detailed assessment for RPM | Leverage Sara's UPI report for action planning; identify deliberate timings
14 | Supplier Inbound | Frequent Changes in Fixed production schedule | Daily |  |  | Demand Surge + No safety protection | Incorporate Inventory at supplier + review Inv target at P&G Labels, Bottle & Pumps - Review Safety Target Setting at Supplier | 1) Review base/ current inventory strategy at suppliers and compare vs. usage requirements in P&G 2) Use MIM to identify the target safety for the supplier | Letty. Connie | May - Supplier Invty
15 | Supplier Inbound | Frequent Changes in Fixed production schedule | Daily |  |  | Demand Surge + No safety protection | Generic shippers | Increase volume for generic shippers; define cost and feasibility assessment | Letty. Connie | May - Supplier Invty
15 | Supplier Inbound | Frequent Changes in Fixed production schedule | Daily |  |  |  | Operational Excellence Elevation | Monthly POSS review - to assess warehouse capcity vs Prima Target Warehouse - Check for Digital RCCP solutions or E2E RCCP Solution | Planning & WH | Starting June
16 | Supplier Inbound | Frequent Changes in Fixed production schedule | Daily |  |  | Demand Surge + No safety protection | To confirm if the JIT strategy is correct Shipper - Incorporate Inventory at supplier + review Inv target at P&G Labels, Bottle & Pumps - Review Safety Target Setting at Supplier | Shipper: Use Prima to identify the P&G Safety Setting | Shivangi | May '26
17 | Warehouse | Warehouse constraint | Daily |  |  |  |  | Matching of Whse Actual Inventory in Pallets vs. Material Targets and Inventory buckets | Shivangi and Sumontha | May - Whse info
18 | Supplier Inbound | Manual ASN and slotting | Daily |  |  | Productivity and accuracy concerns | Implement E2Open - EASN and Inbound e-Slotting | E2open - EASN Follow-up : how to solve the Invoice Number unique requirement | Letty, Sumontha | OND '26
19 | Supplier Inbound | Manual Short Term + Manual Supportability Confirmation | Daily |  |  | Productivity and accuracy concerns | Implement E2Open - Implement acknowledgement within E2Open | Continue supplier confirmation, Planner to utilize Future State: Farm to Shelf Dashboard, Check Materials at risk E2Open implementation | Letty | Oct '26
20 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change Packing MOQ to enable more accurate system recommendations | Change packing MOQ of all lines with 1.5T for CN and 3T for SH, change RV to 1.5T Phase 2: Change the rounding value to 1 cs 2 weeks later | Shyam | 2026-05-22
21 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change Packing MOQ to enable more accurate system recommendations | Design the solver group as per the revised operating strategy ( revised MOQs ) | Saakshi | 2026-05-22
20 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Confirm if solver groups are running correctly - Check for: a) Solver group setting b) Gap closing with penalty setup c) Material constraint for 1 day outside MFZ d) Changeovers vs current state | Saakshi | 2026-05-25
21 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Define planning horizon for FG and CTMZ lines | Saakshi | 2026-05-25
22 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Audit | Check safety stock vs IBPI recommendation | Aman | 2026-05-20
21 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Audit | Audit max stock at a code/DC level | Aman/Jeremy | 2026-05-20
22 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Supplier stock visibility | Setup a NSW for all the label suppliers on OMP | Uma | 2026-06-05
23 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | More accurate capacity planning | For RCCP - take unrestricted demand and then override by EOD with restricted demand | Divya | 2026-05-25
22 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | More accurate capacity planning | OMP - Use phased contrained planning 100%(W1/W2)-> 150%(W3/W4) ->Unrestricted(W5+) | Uma/Gopal | 2026-06-05
23 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Initiative work process improvement | For phase out codes - Trade lane work process - to be discussed
24 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Release Packing POs till D1 4pm ( 2 shifts more vs today ) | Arul | 2026-05-20
23 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Release only corresponding Making POs for the released Packing Pos (Batch sharing to be enabled only for packing converted into purchase orders) | Shyam | 2026-05-20
24 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | STOP releasing with missing parts ( exception for weekend may be 1/2 PMs ) | Arul | 2026-05-20
25 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Work process setup | Align drumbeat meeting for OMP Adherence review | Aniket,Emma | 2026-05-15
24 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Work process setup | Review Shipper and Labels SSP in the OMP adherence supplier PDCA | Shivangi/Letty | 2026-05-20
25 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Labels - Operating strategy, PRIMA Safety reco, Call off strategy(7D- Daily, 14D-Weekly, 30D- Monthly and RCCP assessment of storage room | Shivangi | 2026-05-25
26 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Audit | Audit all PDT and GR on all labels | Pawan/Uma | 2026-05-20
25 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Audit | Audit report for PDT and GR for materials automation | Gowthami | 2026-06-15
26 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | LT offset 2 days on the DepReq for all labels and shippers | Uma | 2026-05-25
27 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Sequence zone - 0 | Arul | 2026-06-30
26 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Work process setup | Drop 24hrs from Tues 4pm to Wed 4pm and run group sort solver | Arul | 2026-05-20
27 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Work process setup | WIP POs tracking in Themis to be excluded | Saakshi/Emma | 2026-05-30
28 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Constrained planning on materials only for 1 day after Tues 4pm | Saakshi | 2026-05-25
27 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | To implement automatic line delay functionality in OMP | Saakshi | 2026-05-25
28 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Run only F2.0 solver and stop running the WIP replenishment solver - Testing | Arul | 2026-05-25
29 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Work process setup | While removing any code from Gantt, don't delete but rather move it to Volume planning | Arul | 2026-05-20
30 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Audit | Audit IVY accuracy for Supplier inputs | Letty | 2026-05-30
31 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Lead time reduction | Shipper WALT reduction to 1 day | Letty | 2026-06-15
32 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Audit | GRPT at 1 day for all B6 PMs | Uma | 2026-05-19
33 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Supplier stock visibility | NSW updated for all JIT materials | Uma | 2026-06-15
34 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Audit | Cycle strategy audit for B6 | Arul | 2026-05-20
35 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | RCCP for Conditioner Capacity - what is the YoY growth assumption? | Shivangi | 2026-05-31
36 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | LRCP for Conditioner Capacity - is 24/7 enough for FY2728 or do we need a new making system? | Shivangi | 2026-06-15
37 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | 18M RCCP - Evaluate options for CND making which would allow making to always follow packing (shift pattern/ staffing / systems?) | Shivangi | 2026-06-15
38 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | 13 week - CND/SH - evaluate operating strategy for repeaters and strangers to offload making systems | Aniket/Emma | 2026-05-15
39 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | Assumption on 12T/6T salience on Conditioner System (Post Beads) | Shivangi | 2026-05-30
40 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | Share how the 17b/day for 5 days per month can be supported on CND | Near | 2026-05-18
41 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | Weekly RCCP at a system making level | Shivangi | 2026-05-25
42 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Define Leadtime for operating strategy enablmenet of 17 batches/day | Shivangi/Boston | 2026-05-25
43 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Change in Operating Strategy | Propose change to POSS to flatten making requirements. Quantify cost/cash impact | Aniket/Emma | 2026-05-18
44 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | How to operationalize the 17 batches vs 15 batches in Plan and Go | Aniket/Shivangi | 2026-05-19
45 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Work process improvement | Process with SUL, TRL, SIP for qualification matrix definition and Delegation | Shivangi, Suree | 2026-06-01
46 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | 190 FIL, system qualfication Assessment on need with initaitive | Suree | 2026-06-01
47 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | Qualification of 13 Top Volume High BCT FILs, across all the systems. And Plan for 32 FILs qualification | Shivangi/Atsiri | 2026-05-25
48 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | Maximizing 12T Ratio on 12T Shampoo systems, or via Sequence balancing | Divya | 2026-06-01
49 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Capacity Improvement | Enable 101 Batches at daily level, via WPI, staffing | Viju, P'Art | 2026-07-01
50 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Audit | Update Qualification matrix in the FIL capability file | Shivangi | 2026-05-25
51 | Planning - THEMIS | Manual Planning |  |  |  | System and Work process inaccuracy | Centreline Management | Bring back storage tank to Centreline | Shyam | 2026-06-15

## Examples
_____ P&G ____ CURRENT STATE
|  | 1 | Cancellation should be executed before 48 hrs
|  | 2 | two truck are waiting
|  | 3 | Although capacity is 150 tons we have 250 tons
replenishment RTT yapılabilir mi?
cancell 48 hrs
SALT SUPPLIER
I
ALKİM
Allocation: 400 tons/month
Location: Afyon
Order Frq: Daily
Opportunity:
335 tl/kg
Storage loc: Afyon
Lead Time: 24 hrs
MOQ: 26 tons
Transit Time: 8 hrs
Avr Montly Order Q: tons
Mntly avr Order 2810 Tons
Yearly spent Pool:
MRP PLANNING
P&G PSC RPM
Schedule Sharing: weekly based
LEGEND
I
*Manuel Info Flow
*Digital Info Flow
*Material Flow
*Pushed Material Flow
*Inventory
Days
Days
Days
Hrs
?
Hrs
LEAD
TIME:
INVENTORY:
Tons
Tons
150 Tons
DAYS
TONS
Average Material LT
LT
Transit Time
Unloading Time
NVA-R
NVA-R
NVA-R
500 Km
550 Km
ADDMIX
Consumption: 96 tons/day
C/T Loading: ? Mins
Unload Schedule: 6 D / 8 H
Inv.:
Operation: ? FTE
SALT SUPPLIER
MUTLUCAN
Allocation: 2410 tons/month
Locaton: Ankara
Order Frq: Daily
Opportunity:
335 tl/kg
Storage loc: Ankara
Lead Time: 24 hrs
MOQ: 26 tons
Transit Time: 9 hrs
Avr Montly Order Q: tons
1

## PointerStorage (hidden)
Note: Plese don't change the values of this Sheet!
Ribbon | 541903760
Excel App | 435101608
Excel Window | 661892
Excel Controls | 346183296